## Describes
****** PLANS FOR PROJECT ******
***** TASKS *****
· SCENES: 1
· POPUPS: 12
o MAIN
o STORIES
o STAGE
o DAILY GIFT
o SHOP
o GAME PLAY
o PAUSE
o GAME OVER
o SUCCESS/FAIL
o MISSION
o MISSION DETAIL
o RESULT
· FUNCTIONS:
o Handling script per Popup ~ 12 scripts
o InAppPurcharseManager for In-app purchase in Shop
o AdsManager for control advertising in game: enalble, disable, number display, max display, limit display, time dipslay, Finish -> get reward, etc…
o TimerManager for control and display time:
§ ads remaining time
§ auto change other function
o NotificationManager:
§ Notify per support item: short, long, power, slow, Mission
§ Notify from client:
· user don’t go back game long time
· items are bought in shop
§ Notify from server
o GameSave to save user’s data to local, or connect to server to save user’
· ART: Create Sprite Atlas to optimize draw call:
o BgAtlas: include images in “BG” and ”BG_basic” folder
o CharacterAtlas: include images in ”characters” folder
o MainAtlas: include images in ”maingame” folder
o MenuAtlas: include images in ” menugame” folder
o OtherAtlas: include images from “effect” and “target” folder
· DATA:
o Create “LevelInfo” json file: to define requirements per level
****** IMPROVE *****
· Social: connect social to login, invite friends to play game: Facebook, Zalo,…
· Build server game or use Firebase as server game to:
o Authen
o Save users info
o Save data game
o Save const

## Tasks
****** PLANS FOR PROJECT ******
STT | DO LIST | DETAILS |  | DEV |  |  | ESTIMATE TIME
|  |  |  | Lead | Dev 1 | Dev 2
1 | TASKS | POPUPS (12) | o MAIN |  | P
2 |  |  | o STORIES |  | P
3 |  |  | o STAGE |  | P
4 |  |  | o DAILY GIFT |  | P
5 |  |  | o SHOP | P
6 |  |  | o GAME PLAY | P
7 |  |  | o PAUSE |  |  | P
8 |  |  | o GAME OVER |  |  | P
9 |  |  | o SUCCESS/FAIL |  |  | P
10 |  |  | o MISSION | P
11 |  |  | o MISSION DETAIL | P
12 |  |  | o RESULT |  |  | P
13 |  | FUNCTIONS (21) | o Handling script per Popup ~ 12 scripts
14 |  |  | o ResourceManager: load map data, load sprite atlas
15 |  |  | o InAppPurcharseManager for In-app purchase in Shop
16 |  |  | o AdsManager for control advertising in game: enalble, disable, number display, max display, limit display, time dipslay, Finish -> get reward, etc…
17 |  |  | o TimerManager for control and display time:
18 |  |  | § ads remaining time
19 |  |  | § auto change other function
20 |  |  | o NotificationManager:
21 |  |  | § Notify per support item: short, long, power, slow, Mission
22 |  |  | § Notify from client:
23 |  |  | · user don’t go back game long time
24 |  |  | · items are bought in shop
25 |  |  | § Notify from server
26 |  |  | o GameSave to save user’s data to local, or connect to server to save user’
27 |  | ART (Create Sprite Atlas to optimize draw call) | o BgAtlas: include images in “BG” and ”BG_basic” folder
28 |  |  | o PopupAtlas: include images in "popup_game" folder
29 |  |  | o CharacterAtlas: include images in ”characters” folder
30 |  |  | o MainAtlas: include images in ”maingame” folder
31 |  |  | o MenuAtlas: include images in ” menugame” folder
32 |  |  | o OtherAtlas: include images from “effect” and “target” folder
33 |  | DATA
34 |  |  | o Create “LevelInfo” json file: to define requirements per level
35
36 | IMPROVE | SOCIAL
37 |  |  | · Social: connect social to login, invite friends to play game: Facebook, Zalo,…
38
39 |  | SERVER (Build server game or use Firebase as Sever game)
40 |  |  | o Authen
41 |  |  | o Save users info
42 |  |  | o Save data game
43 |  |  | o Save const